## Workplan Summary
Workplan |  | Application Identifier: 2020/OCH/0000 |  | Project Title: FOGO collection
Project Summary
No. | Milestone |  | Start | Finish
1 | Signing of the Deed of Agreement |  | 2022-01-31 | 2022-02-28
| No. | Activities | Start | Finish | Grant | Cash | In-Kind | Total
| 1 | Signed Deed of Agreement | 2022-01-31 | 2022-02-28 | 200912 | 5932 | 0 | 206844
| 2 | Any documentation required as a special condition | 2022-01-31 | 2022-02-28 | 0 | 0 | 0 | 0
| 3 | Tax invoice to the NSW Environmental Trust for the instalment amount | 2022-01-31 | 2022-02-28 | 0 | 0 | 0 | 0
|  |  |  | Total: | 200912 | 5932 | 0 | 206844
No. | Milestone |  | Start | Finish
2 | Education and Communication plan |  | 2022-03-01 | 2022-04-30
| No. | Activities | Start | Finish | Grant | Cash | In-Kind | Total
| 1 | Evidence that your Education and Communication plan has been approved by the EPA. | 2022-03-01 | 2022-04-30 | 80365 | 2373 | 0 | 82738
| 2 | Any documentation required as a special condition | 2022-03-01 | 2022-04-30 | 0 | 0 | 0 | 0
| 3 | Copies of tax invoices/quotes from bin suppliers and assembly contractors. | 2022-03-01 | 2022-04-30 | 0 | 0 | 0 | 0
| 4 | Copies of tax invoices/quotes from all other related service providers, suppliers, contractors. | 2022-03-01 | 2022-04-30 | 0 | 0 | 0 | 0
| 5 | Completed Statement of Expenditure (progress) attached as supporting document. | 2022-03-01 | 2022-04-30 | 0 | 0 | 0 | 0
| 6 | Tax invoice to the NSW Environmental Trust for the instalment amount | 2022-03-01 | 2022-04-30 | 0 | 0 | 0 | 0
|  |  |  | Total: | 80365 | 2373 | 0 | 82738
No. | Milestone |  | Start | Finish
3 | Implementation |  | 2022-05-01 | 2022-12-30
| No. | Activities | Start | Finish | Grant | Cash | In-Kind | Total
| 1 | Evidence of educational materials provided to residents. | 2022-05-01 | 2022-12-30 | 80365 | 2373 | 0 | 82738
| 2 | Any documentation required as a special condition | 2022-05-01 | 2022-12-30 | 0 | 0 | 0 | 0
| 3 | Documentation supporting implementation of project (e.g. delivery of bins, start of collections, photos, videos etc.). | 2022-05-01 | 2022-12-30 | 0 | 0 | 0 | 0
| 4 | Description of service commencement | 2022-05-01 | 2022-12-30 | 0 | 0 | 0 | 0
| 5 | Copies of tax invoices from bin suppliers and assembly contractors. | 2022-05-01 | 2022-12-30 | 0 | 0 | 0 | 0
| 6 | Copies of tax invoices from all other related service providers, suppliers, contractors. | 2022-05-01 | 2022-12-30 | 0 | 0 | 0 | 0
| 7 | Completed Statement of Expenditure (progress) attached as supporting document. | 2022-05-01 | 2022-12-30 | 0 | 0 | 0 | 0
| 8 | Tax invoice to the NSW Environmental Trust for the instalment amount | 2022-05-01 | 2022-12-30 | 0 | 0 | 0 | 0
|  |  |  | Total: | 80365 | 2373 | 0 | 82738
No. | Milestone |  | Start | Finish
4 | Six-Month Post Service Commencement |  | 2023-01-01 | 2023-06-30
| No. | Activities | Start | Finish | Grant | Cash | In-Kind | Total
| 1 | Documentation supporting completion of project (e.g. delivery of bins, start of collections, photos, videos etc.). | 2023-01-01 | 2023-06-30 | 40182 | 1187 | 0 | 41369
| 2 | Any documentation required as a special condition | 2023-01-01 | 2023-06-30 | 0 | 0 | 0 | 0
| 3 | Case study for projects involving MUDs | 2023-01-01 | 2023-06-30 | 0 | 0 | 0 | 0
| 4 | Copies of tax invoices from all other related service providers, suppliers, contractors. | 2023-01-01 | 2023-06-30 | 0 | 0 | 0 | 0
| 5 | Tax invoice to the NSW Environmental Trust for the instalment amount | 2023-01-01 | 2023-06-30 | 0 | 0 | 0 | 0
| 6 | Completed and certified Statement of Expenditure (final) audited by an independent auditor (or CFO for local government entities) | 2023-01-01 | 2023-06-30 | 0 | 0 | 0 | 0
| 7 | Tax invoice to the NSW Environmental Trust for the instalment amount | 2023-01-01 | 2023-06-30 | 0 | 0 | 0 | 0
| 8 | 6-month Post Implementation Report | 2023-01-01 | 2023-06-30 | 0 | 0 | 0 | 0
|  |  |  | Total: | 40182 | 1187 | 0 | 41369
|  |  |  | Overall Total: | 401824 | 11865 | 0 | 413689

## Workplan
Workplan |  | Application Identifier: | 2021/OCH/0000 | Project Title: | Fogo collection
Project Outcomes
No. | Outcome | Description
1 | Establishment of a new FOGO Collection Service | Establishment of a new FOGO Collection service to 6,000 households
2 | Diversion of 500 tonnes p.a. of organic waste | Diversion of 500 tonnes per year of source separated food and garden waste with <1% contamination and with >90% householder participation and satisfaction.
Project Schedule
No. | Milestone |  | Start | Finish | Outcome IDs
1 | Signing of the Deed of Agreement |  | 2022-01-31 | 2022-02-28 | 1: Establishment of a new FOGO Collection Service
| No. | Activities | Start | Finish
| 1 | Signed Deed of Agreement | 2022-01-31 | 2022-02-28
| 2 | Any documentation required as a special condition | 2022-01-31 | 2022-02-28
| 3 | Tax invoice to the NSW Environmental Trust for the instalment amount | 2022-01-31 | 2022-02-28
2 | Education and Communication plan |  | 2022-03-01 | 2022-04-30 | 1: Establishment of a new FOGO Collection Service 2: Diversion of 500 tonnes per year of source separated food and garden waste with <1% contamination and with >90% householder participation and satisfaction.
| No. | Activities | Start | Finish
| 1 | Evidence that your Education and Communication plan has been approved by the EPA. | 2022-03-01 | 2022-04-30
| 2 | Any documentation required as a special condition | 2022-03-01 | 2022-04-30
| 3 | Copies of tax invoices/quotes from bin suppliers and assembly contractors. | 2022-03-01 | 2022-04-30
| 4 | Copies of tax invoices/quotes from all other related service providers, suppliers, contractors. | 2022-03-01 | 2022-04-30
| 5 | Completed Statement of Expenditure (progress) attached as supporting document. | 2022-03-01 | 2022-04-30
| 6 | Tax invoice to the NSW Environmental Trust for the instalment amount | 2022-03-01 | 2022-04-30
3 | Implementation |  | 2022-05-01 | 2022-12-30 | 1: Establishment of a new FOGO Collection Service 2: Diversion of 500 tonnes per year of source separated food and garden waste with <1% contamination and with >90% householder participation and satisfaction.
| No. | Activities | Start | Finish
| 1 | Evidence of educational materials provided to residents. | 2022-05-01 | 2022-12-30
| 2 | Any documentation required as a special condition | 2022-05-01 | 2022-12-30
| 3 | Documentation supporting implementation of project (e.g. delivery of bins, start of collections, photos, videos etc.). | 2022-05-01 | 2022-12-30
| 4 | Description of service commencement | 2022-05-01 | 2022-12-30
| 5 | Copies of tax invoices from bin suppliers and assembly contractors. | 2022-05-01 | 2022-12-30
| 6 | Copies of tax invoices from all other related service providers, suppliers, contractors. | 2022-05-01 | 2022-12-30
| 7 | Completed Statement of Expenditure (progress) attached as supporting document. | 2022-05-01 | 2022-12-30
| 8 | Tax invoice to the NSW Environmental Trust for the instalment amount | 2022-05-01 | 2022-12-30
4 | Six-Month Post Service Commencement |  | 2023-01-01 | 2023-06-30 | 1: Establishment of a new FOGO Collection Service 2: Diversion of 500 tonnes per year of source separated food and garden waste with <1% contamination and with >90% householder participation and satisfaction.
| No. | Activities | Start | Finish
| 1 | Documentation supporting completion of project (e.g. delivery of bins, start of collections, photos, videos etc.). | 2023-01-01 | 2023-06-30
| 2 | Any documentation required as a special condition | 2023-01-01 | 2023-06-30
| 3 | Case study for projects involving MUDs | 2023-01-01 | 2023-06-30
| 4 | Copies of tax invoices from all other related service providers, suppliers, contractors. | 2023-01-01 | 2023-06-30
| 5 | Tax invoice to the NSW Environmental Trust for the instalment amount | 2023-01-01 | 2023-06-30
| 6 | Completed and certified Statement of Expenditure (final) audited by an independent auditor (or CFO for local government entities) | 2023-01-01 | 2023-06-30
| 7 | Tax invoice to the NSW Environmental Trust for the instalment amount | 2023-01-01 | 2023-06-30
| 8 | 6-month Post Implementation Report | 2023-01-01 | 2023-06-30
Project Measures
No. | Milestone
1 | Signing of the Deed of Agreement
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 1 | Signed Deed of Agreement | Ongoing project item | measures to be reported at end of project | 0 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 2 | Any documentation required as a special condition | Ongoing project item | measures to be reported at end of project | 0 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 3 | Tax invoice to the NSW Environmental Trust for the instalment amount | Ongoing project item | measures to be reported at end of project | 0 | Number
No. | Milestone
2 | Education and Communication plan
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 1 | Evidence that your Education and Communication plan has been approved by the EPA. | Ongoing project item | measures to be reported at end of project | 0 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 2 | Any documentation required as a special condition | Ongoing project item | measures to be reported at end of project | 0 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 3 | Copies of tax invoices/quotes from bin suppliers and assembly contractors. | Ongoing project item | measures to be reported at end of project | 0 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 4 | Copies of tax invoices/quotes from all other related service providers, suppliers, contractors. | Ongoing project item | measures to be reported at end of project | 0 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 5 | Completed Statement of Expenditure (progress) attached as supporting document. | Ongoing project item | measures to be reported at end of project | 0 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 6 | Tax invoice to the NSW Environmental Trust for the instalment amount | Ongoing project item | measures to be reported at end of project | 0 | Number
No. | Milestone
3 | Implementation
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 1 | Evidence of educational materials provided to residents. | Ongoing project item | measures to be reported at end of project | 0 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 2 | Any documentation required as a special condition | Ongoing project item | measures to be reported at end of project | 0 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 3 | Documentation supporting implementation of project (e.g. delivery of bins, start of collections, photos, videos etc.). | Ongoing project item | measures to be reported at end of project | 0 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 4 | Description of service commencement | Ongoing project item | measures to be reported at end of project | 0 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 5 | Copies of tax invoices from bin suppliers and assembly contractors. | Ongoing project item | measures to be reported at end of project | 0 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 6 | Copies of tax invoices from all other related service providers, suppliers, contractors. | Ongoing project item | measures to be reported at end of project | 0 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 7 | Completed Statement of Expenditure (progress) attached as supporting document. | Ongoing project item | measures to be reported at end of project | 0 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 8 | Tax invoice to the NSW Environmental Trust for the instalment amount | Ongoing project item | measures to be reported at end of project | 0 | Number
No. | Milestone
4 | Six-Month Post Service Commencement
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 1 | Documentation supporting completion of project (e.g. delivery of bins, start of collections, photos, videos etc.). | Ongoing project item | measures to be reported at end of project | 0 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 2 | Any documentation required as a special condition | Ongoing project item | measures to be reported at end of project | 0 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 3 | Case study for projects involving MUDs | Ongoing project item | measures to be reported at end of project | 0 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 4 | Copies of tax invoices from all other related service providers, suppliers, contractors. | Ongoing project item | measures to be reported at end of project | 0 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 5 | Tax invoice to the NSW Environmental Trust for the instalment amount | Ongoing project item | measures to be reported at end of project | 0 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 6 | Completed and certified Statement of Expenditure (final) audited by an independent auditor (or CFO for local government entities) | Ongoing project item | measures to be reported at end of project | 0 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 7 | Tax invoice to the NSW Environmental Trust for the instalment amount | Ongoing project item | measures to be reported at end of project | 0 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 8 | 6-month Post Implementation Report | End of Project Reporting | Number of grant funded staff | 1 | Number
|  |  |  | Number of hours (grant funded) | 400 | Number
|  |  |  | Number of grant funded consultants/contractors | 2 | Number
|  |  |  | Number of hours (grant funded consultants/contractors) | 600 | Number
|  |  |  | Number of non grant funded staff | 4 | Number
|  |  |  | Number hours (non grant funded) | 1000 | Number
|  |  |  | Number of volunteers | 0 | Number
|  |  |  | Number of hours (volunteers) | 0 | Number
|  |  |  | New ongoing jobs created | 1 | Number
|  |  |  | New ongoing jobs created - hours | 400 | Number
|  |  |  | Additional household organics diverted | 1000 | Tonnes
|  |  |  | Additional households with a new bin based service | 6000 | Number
|  |  |  | Mobile Garbage Bins (MGBs) purchased with grant funding. | 6000 | Number
|  |  |  | Households with a new food or combined food and garden service | 6000 | Number
|  |  |  | Kitchen caddies purchased with grant funding | 6000 | Number
|  |  |  | Participation rate - households using the bin provided | 90 | Percentage
|  |  |  | Estimated contamination rate | 1 | Percentage
|  |  |  | Delivering awareness raising events and training - number of events | 8 | Number
|  |  |  | Delivering awareness raising events and training - number of participants/attendees | 10000 | Number
|  |  |  | Developing educational products/resources - No. developed and distributed | 7 | Number
|  |  |  | Developing educational products/resources - Individuals potentially reached | 10000 | Number
|  |  |  | Funding spent with NSW Suppliers ($) | 332858 | Dollars
|  |  |  | Processing cost per tonne of material collected ($ per tonne) | 35 | Dollars
|  |  |  | Bin lift Cost ($ per lift) | 1.2 | Dollars
|  |  |  | Additional lifts per year (not applicable to Multi Unit Dwellings (MUDs) | 52 | Number
Project Budget
|  |  | Whole Total: | 401824 | 11865 | 0 | 413689
No | Milestone
1 | Signing of the Deed of Agreement
| No | Activities | Description | Grant | Cash | In-Kind | Total
| 1 | Signed Deed of Agreement | Signed Deed of Agreement | 200912 | 5932 | 0 | 206844
| 2 | Any documentation required as a special condition | Any documentation required as a special condition | 0 | 0 | 0 | 0
| 3 | Tax invoice to the NSW Environmental Trust for the instalment amount | Tax invoice to the NSW Environmental Trust for the instalment amount | 0 | 0 | 0 | 0
|  |  | Total: | 200912 | 5932 | 0 | 206844
No | Milestone
2 | Education and Communication plan
| No | Activities | Description | Grant | Cash | In-Kind | Total
| 1 | Evidence that your Education and Communication plan has been approved by the EPA. | Evidence that your Education and Communication plan has been approved by the EPA. | 80365 | 2373 | 0 | 82738
| 2 | Any documentation required as a special condition | Any documentation required as a special condition | 0 | 0 | 0 | 0
| 3 | Copies of tax invoices/quotes from bin suppliers and assembly contractors. | Copies of tax invoices/quotes from bin suppliers and assembly contractors. | 0 | 0 | 0 | 0
| 4 | Copies of tax invoices/quotes from all other related service providers, suppliers, contractors. | Copies of tax invoices/quotes from all other related service providers, suppliers, contractors. | 0 | 0 | 0 | 0
| 5 | Completed Statement of Expenditure (progress) attached as supporting document. | Completed Statement of Expenditure (progress) attached as supporting document. | 0 | 0 | 0 | 0
| 6 | Tax invoice to the NSW Environmental Trust for the instalment amount | Tax invoice to the NSW Environmental Trust for the instalment amount | 0 | 0 | 0 | 0
|  |  | Total: | 80365 | 2373 | 0 | 82738
No | Milestone
3 | Implementation
| No | Activities | Description | Grant | Cash | In-Kind | Total
| 1 | Evidence of educational materials provided to residents. | Evidence of educational materials provided to residents. | 80365 | 2373 | 0 | 82738
| 2 | Any documentation required as a special condition | Any documentation required as a special condition | 0 | 0 | 0 | 0
| 3 | Documentation supporting implementation of project (e.g. delivery of bins, start of collections, photos, videos etc.). | Documentation supporting implementation of project (e.g. delivery of bins, start of collections, photos, videos etc.). | 0 | 0 | 0 | 0
| 4 | Description of service commencement | Description of service commencement | 0 | 0 | 0 | 0
| 5 | Copies of tax invoices from bin suppliers and assembly contractors. | Copies of tax invoices from bin suppliers and assembly contractors. | 0 | 0 | 0 | 0
| 6 | Copies of tax invoices from all other related service providers, suppliers, contractors. | Copies of tax invoices from all other related service providers, suppliers, contractors. | 0 | 0 | 0 | 0
| 7 | Completed Statement of Expenditure (progress) attached as supporting document. | Completed Statement of Expenditure (progress) attached as supporting document. | 0 | 0 | 0 | 0
| 8 | Tax invoice to the NSW Environmental Trust for the instalment amount | Tax invoice to the NSW Environmental Trust for the instalment amount | 0 | 0 | 0 | 0
|  |  | Total: | 80365 | 2373 | 0 | 82738
No | Milestone
4 | Six-Month Post Service Commencement
| No | Activities | Description | Grant | Cash | In-Kind | Total
| 1 | Documentation supporting completion of project (e.g. delivery of bins, start of collections, photos, videos etc.). | Documentation supporting completion of project (e.g. delivery of bins, start of collections, photos, videos etc.). | 40182 | 1187 | 0 | 41369
| 2 | Any documentation required as a special condition | Any documentation required as a special condition | 0 | 0 | 0 | 0
| 3 | Case study for projects involving MUDs | Case study for projects involving MUDs | 0 | 0 | 0 | 0
| 4 | Copies of tax invoices from all other related service providers, suppliers, contractors. | Copies of tax invoices from all other related service providers, suppliers, contractors. | 0 | 0 | 0 | 0
| 5 | Tax invoice to the NSW Environmental Trust for the instalment amount | Tax invoice to the NSW Environmental Trust for the instalment amount document. | 0 | 0 | 0 | 0
| 6 | Completed and certified Statement of Expenditure (final) audited by an independent auditor (or CFO for local government entities) | Completed and certified Statement of Expenditure (final) audited by an independent auditor (or CFO for local government entities) | 0 | 0 | 0 | 0
| 7 | Tax invoice to the NSW Environmental Trust for the instalment amount | Tax invoice to the NSW Environmental Trust for the instalment amount | 0 | 0 | 0 | 0
| 8 | 6-month Post Implementation Report | 6-month Post Implementation Report | 0 | 0 | 0 | 0
|  |  | Total: | 40182 | 1187 | 0 | 41369