## Workplan Summary
Workplan |  | Application Identifier: | 2024/FMP/0003 | Project Title: | Sample City - Flood risk management plan
Project Summary
No. | Milestone |  | Start | Finish
1 | Data collection and analysis |  | 3/02/2025 | 12/09/2025
| No. | Activities | Start | Finish | Grant Contribution | Grantee Contribution | Partner Contribution | Total
| 1 | FRM committee inception meeting | ​03/02/2025 | 12/09/2025 | 400 | 200 | 0 | 600
| 2 | Data collection Update model and flood level survey (optional) | ​03/02/2025 | 12/09/2025 | 30267 | 15133 | 0 | 45400
|  |  |  | Total: | 30667 | 15333 | 0 | 46000
No. | Milestone |  | Start | Finish
2 | Flood damages and hazard identification |  | 15/09/2025 | ​08/01/2026
| No. | Activities | Start | Finish | Grant Contribution | Grantee Contribution | Partner Contribution | Total
| 1 | Flood damages assessment | 15/09/2025 | ​08/01/2026 | 21333 | 10667 | 0 | 32000
| 2 | Flood planning measures and mapping | 15/09/2025 | ​08/01/2026 | 26800 | 13400 | 0 | 40200
| 3 | Progress Report | 15/09/2025 | ​08/01/2026 | 4500 | 2250 | 0 | 6750
|  |  |  | Total: | 52633 | 26317 | 0 | 78950
No. | Milestone |  | Start | Finish
3 | Public exhibition of Draft FRMP |  | 12/01/2026 | 29/05/2026
| No. | Activities | Start | Finish | Grant Contribution | Grantee Contribution | Partner Contribution | Total
| 1 | FRM committee meeting | 12/01/2026 | 29/05/2026 | 400 | 200 | 0 | 600
| 2 | Agency consultation | 12/01/2026 | 29/05/2026 | 800 | 400 | 0 | 1200
| 3 | Draft FRMP on exhibition | 12/01/2026 | 29/05/2026 | 1533 | 767 | 0 | 2300
|  |  |  | Total: | 2733 | 1367 | 0 | 4100
No. | Milestone |  | Start | Finish
4 | Final Flood risk management plan (FRMP) |  | 1/06/2026 | 10/12/2026
| No. | Activities | Start | Finish | Grant Contribution | Grantee Contribution | Partner Contribution | Total
| 1 | Assess submissions of DRAFT | ​01/06/2026 | 10/12/2026 | 5000 | 2500 | 0 | 7500
| 2 | FRM Committee meeting | ​01/06/2026 | 10/12/2026 | 400 | 200 | 0 | 600
| 3 | Final FRMP to Council for adoption | ​01/06/2026 | 10/12/2026 | 1533 | 767 | 0 | 2300
| 4 | FRMP adopted Handover of data | ​01/06/2026 | 10/12/2026 | 0 | 0 | 0 | 0
|  |  |  | Total: | 6933 | 3467 | 0 | 10400
|  |  |  | Overall Total: | 92966 | 46484 | 0 | 139450

## Workplan
Workplan |  | Application Identifier: | 2024/FMP/0003 | Project Title: | Sample City - Flood risk management plan
Project Outcomes
No. | Outcome | Description
1 | Flood risk management study and plan (FRMP) | Produce a FRMP to identify risk management options to address the flood risk to over 105 properties within the Sample City catchment
2 | Reduce risk of flooding | Reduce the risk of flooding by identifying the most appropriate planning controls and required emergency response.
3 | Community engagement and awareness | Gaining the engagement of the community in managing flood risk
Project Schedule
No. | Milestone |  | Start | Finish | Outcome IDs
1 | Data collection and analysis |  | 3/02/2025 | 12/09/2025 | 1
| No. | Activities | Start | Finish
| 1 | FRM committee inception meeting | 3/02/2025 | 12/09/2025
| 2 | Data collection Update model and flood level survey (optional) | 3/02/2025 | 12/09/2025
2 | Flood damages and hazard identification |  | 15/09/2025 | 8/01/2026 | 1
| No. | Activities | Start | Finish
| 1 | Flood damages assessment | 15/09/2025 | 8/01/2026
| 2 | Flood planning measures and mapping | 15/09/2025 | 8/01/2026
| 3 | Progress Report | 15/09/2025 | 8/01/2026
3 | Public exhibition of Draft FRMP |  | 12/01/2026 | 29/05/2026 | 1, 3
| No. | Activities | Start | Finish
| 1 | FRM committee meeting | 12/01/2026 | 29/05/2026
| 2 | Agency consultation | 12/01/2026 | 29/05/2026
| 3 | Draft FRMP on exhibition | 12/01/2026 | 29/05/2026
4 | Final Flood risk management plan (FRMP) |  | 1/06/2026 | 10/12/2026 | 1, 2, 3
| No. | Activities | Start | Finish
| 1 | Assess submissions of DRAFT | 1/06/2026 | 10/12/2026
| 2 | FRM Committee meeting | 1/06/2026 | 10/12/2026
| 3 | Final FRMP to Council for adoption | 1/06/2026 | 10/12/2026
| 4 | FRMP adopted Handover of data | 1/06/2026 | 10/12/2026
Project Measures
No. | Milestone
4 | Final Flood risk management plan (FRMP)
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 1 | Assess submissions of DRAFT | Managing and delivering the project (include human resourcing for implementation, collaboration, etc)* | Number of grant funded staff | 0 | Number
|  |  |  | Number of hours (grant funded) | 0 | Number
|  |  |  | Number of grant funded consultants/contractors | 1 | Number
|  |  |  | Number of hours (grant funded consultants/contractors) | ​500 | Number
|  |  |  | Number of non grant funded staff | 1 | Number
|  |  |  | Number hours (non grant funded) | 30 | Number
|  |  |  | Number of volunteers | 0 | Number
|  |  |  | Number of hours (volunteers) | 0 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 2 | FRM Committee meeting | Prepare or review Flood risk management studies or plans* | Number of flood risk management study and plans completed | 1 | Number
|  |  |  | Number of flood risk management study and plans adopted | 1 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 3 | Final FRMP to Council for adoption | Identify flood mitigation options* | Number of management options identified (high) | 5 | Number
|  |  |  | Number of management options identified (medium) | 5 | Number
|  |  |  | Number of management options identified (low) | 10 | Number
|  |  |  | Number of properties identified as at risk (high) | 21 | Number
|  |  |  | Number of properties identified as at risk (medium) | 45 | Number
|  |  |  | Number of properties identified as at risk (low) | 39 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 4 | FRMP adopted Handover of data | Consult with community and stakeholders to increase understanding of flood issues* | Number of individuals reporting increased awareness of the issue/s | 105 | Number
|  |  |  | Describe the people included here | Residents deemed in risk areas | Free Text (5 to 50 words)
|  |  |  | Number of individuals reporting increased understanding of the issue/s | 105 | Number
Project Budget |  | Selected Ratio: | 33% 2:1
|  |  | Whole Total: | 139450 | 0 | 46484 | 92966
No | Milestone
1 | Data collection and analysis
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | FRM committee inception meeting | Consultant | 600 | 0 | 200 | 400
| 2 | Data collection Update model and flood level survey (optional) | Consultant | 45400 | 0 | 15133 | 30267
|  |  | Total: | 46000 | 0 | 15333 | 30667
No | Milestone
2 | Flood damages and hazard identification
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Flood damages assessment | Consultant | 32000 | 0 | 10667 | 21333
| 2 | Flood planning measures and mapping | Consultant | 40200 | 0 | 13400 | 26800
| 3 | Progress Report | Consultant | 6750 | 0 | 2250 | 4500
|  |  | Total: | 78950 | 0 | 26317 | 52633
No | Milestone
3 | Public exhibition of Draft FRMP
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | FRM committee meeting | Consultant | 600 | 0 | 200 | 400
| 2 | Agency consultation | Consultant | 1200 | 0 | 400 | 800
| 3 | Draft FRMP on exhibition | Consultant | 2300 | 0 | 767 | 1533
|  |  | Total: | 4100 | 0 | 1367 | 2733
No | Milestone
4 | Final Flood risk management plan (FRMP)
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Assess submissions of DRAFT | Consultant | 7500 | 0 | 2500 | 5000
| 2 | FRM Committee meeting | Consultant | 600 | 0 | 200 | 400
| 3 | Final FRMP to Council for adoption | Consultant | 2300 | 0 | 767 | 1533
| 4 | FRMP adopted Handover of data | Not a costed activity | 0 | 0 | 0 | 0
|  |  | Total: | 10400 | 0 | 3467 | 6933